## Client Access Tracker
Client Name | GMB Access | Google Search Console Access | Instagram Access | Facebook Access | Access Status | Priority | Notes
Aqua Treat | Pending | Pending | Given | Unknown | Blocked — Windsor / GA4 / GSC / GBP Verification Missing | High | Prompt 01-03 completed. All access pending. Windsor not yet connected.
Deemax | Unknown | Unknown | Unknown | Unknown | Not Started | Medium | No client-strategy.md. Discovery not yet initiated.
Devmantra | Unknown | Unknown | Unknown | Unknown | Not Started | Medium | No client-strategy.md. Discovery not yet initiated.
Gore Hospital | Blocked (403 — Reauth Required) | Connected (Verify) | Given | Given | Blocked — GBP Reauthorization Required | High | GBP 403 PERMISSION_DENIED. Windsor GBP connector needs reauth. GSC connected but branded_vs_nonbranded field broken. GA4 connected — 0 conversion events; internal traffic polluting data.
Hera Clinic | Unknown | Missing | Given | Given | Blocked — Windsor / GA4 / GSC Access Missing | High | No GSC or GA4. Windsor not connected.
Jeevisha Pain Center | Given | Given | Given | Given | Active — Complete Access | High | Windsor-verified GMB and GSC data.
KUMSS | Pending | Pending | Pending | Given | Discovery Phase | Medium | Prompt 01-03 completed. All platforms pending. Initial discovery stage.
Millennium School | Pending | Pending | Given | Given | Blocked — Windsor / GA4 / GSC / GBP Verification Missing | High | Prompt 01-03 completed. NAP inconsistency (Revaz vs Revas, pin 411033 vs 411057) must be resolved before GBP work. P0: Little Millennium brand contamination on site.
Nakshatra | Blocked by Windsor Plan Limit | Pending Verification | Given | Given | Blocked — Windsor Account Limitation | High | Prompt 01-03 completed. Windsor plan limit blocks GMB connector. GSC and GA4 pending verification. Prompts 04/05 on hold.
Neurosociety Pune | Not Applicable | Pending | Unknown | Given | Partial — SEO Data Access Pending | Medium | Prompt 01-03 completed. Professional medical society — no GBP (no service address, no patient acquisition). GSC/GA4 pending. Prompt 04 on hold for data-backed sections.
NRS | Pending | Pending | Unknown | Unknown | Blocked — Windsor / GA4 / GSC / GBP Verification Missing | High | Prompt 01-03 completed. All access pending. Windsor not yet connected.
Pinnacle Science Academy | Pending | Pending | Unknown | Unknown | Blocked — Windsor / GA4 / GSC / GBP Verification Missing | High | Prompt 01-03 completed. All access pending. Windsor not yet connected.
Pparam | Given | Given | Unknown | Given | Partial — Execution Phase | High | Windsor-verified GMB and GSC data.
Prime Hospital | Given | Given | Given | Given | Active — Complete Access | High | Windsor-verified GMB and GSC data.
Suman Hospital | Given | Given | Given | Given | Active — Complete Access | High | Windsor-verified GMB and GSC data.
The Digitech Solutions | Given (Connected) | Given (Connected) | Given | Given | Active — Complete Access | High | Windsor-verified GMB and GSC data.